## Schedule_Baseline_Plan
Project | Consultant_Contractor | Package | SubPackage_1 | SubPackage_2 | SubPackage_3 | SubPackage_4 | SubPackage_5 | Activity | Critical_Path | Baseline_Planned_Start | Baseline_Planned_Finish
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0040 RETAIL AND F&B |  | 2019-12-16 | 2020-01-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0030 MEP AND IT |  | 2019-12-16 | 2020-01-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0020 STRUCTURAL |  | 2019-12-16 | 2020-01-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0010 ARCHITECTURAL |  | 2019-12-16 | 2020-01-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0120 DEMOLITION SCHEME (AGENCY) |  | 2020-05-02 | 2020-05-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0110 RETROFITTING WORKS |  | 2020-04-28 | 2020-05-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0100 TEMP FACADE |  | 2020-04-14 | 2020-04-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0090 ARCHITECTURAL |  | 2020-02-03 | 2020-03-24
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0080 AIRPORT SYSTEMS |  | 2020-02-01 | 2020-03-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0070 IT (BY DIAL) |  | 2020-02-01 | 2020-03-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0060 STRUCTURAL |  | 2020-02-01 | 2020-03-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0050 HVAC |  | 2020-03-07 | 2020-03-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0040 PHE |  | 2020-03-05 | 2020-03-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0030 FPS AND FDAS |  | 2020-03-03 | 2020-03-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0020 ELECTRICAL |  | 2020-03-03 | 2020-03-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0010 ELV |  | 2020-02-26 | 2020-02-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0120 DEMOLITION SCHEME |  | 2020-05-11 | 2020-05-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0110 RETROFITTING WORKS |  | 2020-05-07 | 2020-05-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0100 TEMP FACADE |  | 2020-04-23 | 2020-04-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0090 ARCHITECTURAL |  | 2020-03-25 | 2020-04-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0080 AIRPORT SYSTEMS |  | 2020-03-11 | 2020-03-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0070 IT (BY DIAL) |  | 2020-03-11 | 2020-03-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0060 STRUCTURAL |  | 2020-04-01 | 2020-04-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0050 HVAC |  | 2020-03-09 | 2020-03-17
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0040 PHE |  | 2020-03-06 | 2020-03-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0030 FPS AND FDAS |  | 2020-03-05 | 2020-03-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0020 ELECTRICAL |  | 2020-03-05 | 2020-03-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0010 ELV |  | 2020-02-27 | 2020-03-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0120 DEMOLITION SCHEME |  | 2020-05-19 | 2020-05-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0110 RETROFITTING WORKS |  | 2020-05-15 | 2020-05-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0100 TEMP FACADE |  | 2020-05-02 | 2020-05-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0090 ARCHITECTURAL |  | 2020-04-02 | 2020-04-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0080 AIRPORT SYSTEMS |  | 2020-03-19 | 2020-03-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0070 IT (BY DIAL) |  | 2020-03-19 | 2020-03-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0060 STRUCTURAL |  | 2020-04-09 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0050 HVAC |  | 2020-03-18 | 2020-03-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0040 PHE |  | 2020-03-16 | 2020-03-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0030 FPS AND FDAS |  | 2020-03-14 | 2020-03-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0020 ELECTRICAL |  | 2020-03-14 | 2020-03-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0010 ELV |  | 2020-03-06 | 2020-03-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00130 DEMOLITION AGENCY - STEEL AND CONCRETE WORKS |  | 2020-02-01 | 2020-04-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00100 AGENCY FOR RETROFITTING WORKS- COLUMN STRENGTHENING |  | 2020-04-14 | 2020-04-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0050 TEMP. FAÇADE AGENCY |  | 2020-03-16 | 2020-03-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0090 AGENCY FOR HVAC WORK |  | 2020-03-23 | 2020-04-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0080 AGENCY FOR FIRE ALARM SYSTEM |  | 2020-03-19 | 2020-04-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0070 AGENCY FOR ELECTRICAL WORK |  | 2020-03-19 | 2020-04-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0060 AGENCY FOR FIRE FIGHTING WORK |  | 2020-03-19 | 2020-03-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0040 AGENCY FOR BMS WORK |  | 2020-03-12 | 2020-03-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0010 AGENCY FOR PHE WORK |  | 2020-03-20 | 2020-03-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00120 AGENCY FOR FINISHES- RESERVED LOUNGE,TM COMPLEX,TICKET COUNT |  | 2020-04-07 | 2020-04-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00110 AGENCY FOR FINISHES- TOILET |  | 2020-04-07 | 2020-04-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0030 AGENCY FOR ELEVATOR - MODIFICATION WORK |  | 2020-03-19 | 2020-03-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0020 AGENCY FOR ELEVATOR - NEW ( PRM LIFT) |  | 2020-03-19 | 2020-03-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0080 DUCT |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0070 CABLE |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0060 PANEL |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0050 AUTOMATIC TRANSFER SWITCH |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00130 VALVES |  | 2020-04-09 | 2020-04-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00120 PIPES |  | 2020-04-09 | 2020-04-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00110 VENTILATION FAN |  | 2020-04-09 | 2020-04-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0090 ELECTRICAL LOW SIDE |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0030 FIRE FIGHTING LOW SIDE |  | 2020-03-31 | 2020-04-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0020 BMS LOW SIDE |  | 2020-03-30 | 2020-04-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00140 HVAC LOW SIDE |  | 2020-04-09 | 2020-04-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00100 FIRE ALARM LOW SIDE |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0010 PHE LOW SIDE |  | 2020-03-28 | 2020-04-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0040 ELEVATOR |  | 2020-03-28 | 2020-04-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00120 RETROFITTING WORKS |  | 2020-05-20 | 2020-06-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0010 MOBILISATION OF DEMOLITION AGENCY |  | 2020-08-17 | 2020-08-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00210 HARD BARRICADING |  | 2020-07-10 | 2020-07-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00200 SOFT PANELS |  | 2020-07-10 | 2020-07-17
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00190 PUFF PANELS |  | 2020-06-24 | 2020-06-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0080 PIPES |  | 2020-04-17 | 2020-05-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0050 DUCT |  | 2020-04-14 | 2020-05-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00160 VENTILATION FANS |  | 2020-04-17 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00150 AUTOMATIC TRANSFER SWITCH |  | 2020-04-14 | 2020-06-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00140 PANEL |  | 2020-04-14 | 2020-06-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00110 CABLE |  | 2020-04-14 | 2020-05-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00100 VALVES |  | 2020-04-17 | 2020-05-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0090 HVAC LOW SIDE |  | 2020-04-25 | 2020-05-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0070 FIRE ALARM LOW SIDE |  | 2020-04-22 | 2020-05-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0060 ELECTRICAL LOW SIDE |  | 2020-04-22 | 2020-05-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0040 FIRE FIGHTING LOW SIDE |  | 2020-04-16 | 2020-05-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0030 BMS LOW SIDE |  | 2020-04-15 | 2020-05-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0020 PHE LOW SIDE |  | 2020-04-06 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00180 RESERVED LOUNGE,TM COMPLEX,TICKET COUNTER, L&F ROOM FINISHES |  | 2020-04-28 | 2020-05-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00170 FINISHES |  | 2020-05-08 | 2020-06-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00130 ELEVATOR - NEW ( PRM LIFT) |  | 2020-04-09 | 2020-06-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0070 PUFF PANEL BARRICADE AT MEZZANINE CORRIDOR - A&C |  | 2020-09-16 | 2020-09-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0060 PUFF PANEL BARRICADE AT DEPARTURE |  | 2020-08-24 | 2020-09-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0050 SOFT PANEL BARRICADE AT DEPARTURE |  | 2020-08-14 | 2020-08-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0040 HARD BARRICADE AROUND 2 SIDES OF T1D BUILDING AT FORECOURT & AI |  | 2020-08-14 | 2020-08-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0030 PUFF PANEL BARRICADE BOARDING GATE AREA - APRON LEVEL |  | 2020-08-11 | 2020-08-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0020 SOFT PANEL BARRICADE BOARDING GATE AREA - APRON LEVEL |  | 2020-08-07 | 2020-08-10
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0010 PUFF PANEL BARRICADE AT BMA |  | 2020-07-01 | 2020-07-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0090 DISMANTLING OF AREA 2 |  | 2020-10-19 | 2020-12-10
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0080 DISMANTLING OF AREA 3 |  | 2020-09-23 | 2020-11-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0070 DISMANTLING OF AREA 1 |  | 2020-09-23 | 2020-10-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0060 STRENGTHENING OF LIFT COLUMN AT K-2 |  | 2020-08-20 | 2020-10-17
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0050 STRENGTHENING OF LIFT COLUMN AT K-9 SUPERSTRUCTURE |  | 2020-06-19 | 2020-08-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0040 STRENGTHENING OF LIFT COLUMN AT K-9 SUBSTRUCTURE |  | 2020-05-20 | 2020-06-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0030 LOCAL BARRICADE AND CLOSURE OF F&B AT GRID K-9 IN TICKET COUNTE |  | 2020-05-14 | 2020-05-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0020 CONVERSION OF DDC AT GRID K-9 ON MANUAL MODE |  | 2020-05-14 | 2020-05-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0010 LOCAL SHIFTING OF EXTRACT FAN AT GRID K-9 |  | 2020-05-14 | 2020-05-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0080 BLOCK WALL & SLAB FOR WASH BASIN |  | 2020-04-10 | 2020-04-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0060 BREAKING OF FALSE CEILING |  | 2020-04-07 | 2020-04-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0050 BREAKING OF TILE |  | 2020-04-02 | 2020-04-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0040 BARRICATION OF BMA TOILET |  | 2020-03-27 | 2020-04-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00200 FINISHING WORK INCL MEP 3RD FIX |  | 2020-05-26 | 2020-06-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00150 PLASTER & WALL TILING |  | 2020-04-27 | 2020-05-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00120 TESTING OF PHE LINE |  | 2020-04-24 | 2020-04-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00100 CHASING AND LAYING OF PHE PIPE |  | 2020-04-17 | 2020-04-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00380 FINISHING WORK INCL MEP 3RD FIX |  | 2020-07-22 | 2020-08-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00330 PLASTER & WALL TILING |  | 2020-07-13 | 2020-07-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00290 TESTING OF PHE LINE |  | 2020-07-08 | 2020-07-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00280 CHASING AND LAYING OF PHE PIPE |  | 2020-07-01 | 2020-07-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00270 BLOCK WALL & SLAB FOR WASH BASIN |  | 2020-06-20 | 2020-06-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00240 BREAKING OF BLOCK WALL FOR MAKING WORKMEN ACCESS FROM BMA |  | 2020-06-13 | 2020-06-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00210 AREA BARRICATION & REMOVAL OF SEATS |  | 2020-06-09 | 2020-06-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00300 MODIFICATION WORKS - FINISHING |  | 2020-06-04 | 2020-07-29
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00220 MODIFICATION WORKS - MEP |  | 2020-05-02 | 2020-06-29
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00170 SLAB CUTOUT AND ACCESS STAIRCASE FOR COR-C ON RHS |  | 2020-05-08 | 2020-06-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00160 CONNECTING PLATFORM TO EXIT STAIRCASE ST-03 FROM MEZZANINE S |  | 2020-05-08 | 2020-06-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00480 FINISHING WORK INCL MEP 3RD FIX |  | 2020-08-29 | 2020-09-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00470 PLASTER & WALL TILING |  | 2020-08-25 | 2020-08-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00460 TESTING OF PHE LINE |  | 2020-08-24 | 2020-08-24
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00450 CHASING AND LAYING OF PHE PIPE |  | 2020-08-20 | 2020-08-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00420 BLOCK WALL & SLAB FOR WASH BASIN |  | 2020-08-17 | 2020-08-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00410 BREAKING OF FALSE CEILING |  | 2020-08-13 | 2020-08-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00400 BREAKING OF TILE |  | 2020-08-10 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00390 BARRICATION OF PRE-SHA TOILET |  | 2020-08-07 | 2020-08-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00350 TESTING & COMMISSIONING OF PRM LIFT |  | 2020-07-23 | 2020-07-29
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00340 LIFT INSTALLATION |  | 2020-06-02 | 2020-07-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0030 BMA AREA WALL DEMOLITION OF LIFT INSTALLATION ACCESS |  | 2020-03-28 | 2020-03-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0020 BARRICATION |  | 2020-03-24 | 2020-03-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00190 ELECTRICAL SUPPLY , SHAFT LIGHTING ETC |  | 2020-05-22 | 2020-05-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00180 LIFT SHAFT & PIT CONNECTION (CIVIL WORKS) |  | 2020-03-31 | 2020-05-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0010 APPROVAL FOR BMA AREA WALL DEMOLITION/BARRICATION |  | 2020-03-19 | 2020-03-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0090 IT WORKS (DIAL) |  | 2020-04-14 | 2020-04-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0070 PROVISION OF POWER SOURCE AT NEW LOCATION |  | 2020-04-07 | 2020-04-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00130 SHIFTING OF MACHINE |  | 2020-04-21 | 2020-04-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00430 INTERNAL FINISHING WORKS |  | 2020-07-03 | 2020-08-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00310 IT WORKS |  | 2020-06-16 | 2020-07-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00260 ELECTRICAL WORKS |  | 2020-06-08 | 2020-06-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00250 CIVIL WORKS (PARTITION INSTALLATION AND CIELING WORKS) |  | 2020-05-04 | 2020-06-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00140 BARRICATION WORKS |  | 2020-04-28 | 2020-05-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00440 INTERNAL FINISHING WORKS |  | 2020-07-20 | 2020-08-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00370 MEP WORKS |  | 2020-07-02 | 2020-07-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00360 IT WORKS |  | 2020-07-02 | 2020-07-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00320 CIVIL WORKS (PARTITION INSTALLATION AND CIELING WORKS) |  | 2020-06-03 | 2020-07-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00230 REMOVAL OF CENTRAL STAIR CASE & SLAB CASTING |  | 2020-04-10 | 2020-06-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00110 BARRICATION |  | 2020-04-02 | 2020-04-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0090 1. INSTALLATION OF NEW ESSENTIAL PANEL AT BMA |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0060 5. TRACING OF EXISTING FLOOR RACEWAY / CONDUIT ABOVE FALSE CE |  | 2020-04-14 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00570 7. REMOVAL OF DBs FEEDING TO VIP CORRIDOR |  | 2020-08-14 | 2020-08-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00530 7. DISCONNECTION AND REMOVAL OF EXISTING PANEL / DBs at RHS |  | 2020-08-11 | 2020-08-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0050 1. CABLE TRAY LAYING WITH EARTHING FROM MSR TO NEW ESSENTIAL |  | 2020-05-11 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00490 8. DISMANTLING OF KITCHEN PANEL |  | 2020-08-14 | 2020-08-17
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00310 6. TRANSFER LOAD ( VRV, AIR CURTAINS AND STARTER) TO NEW ESS |  | 2020-06-29 | 2020-07-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00230 7. 60 KVA UPS DISCONNECTION AT RHS ROOM |  | 2020-06-27 | 2020-06-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00220 4. CABLE TERMINATION & CHARGING OF ESSENTIAL PANEL |  | 2020-06-26 | 2020-06-27
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00210 6. TRANSFER LOAD ( EMERGENCY LIGHTS, SL DOOR, FIDS, GATE COU |  | 2020-06-10 | 2020-06-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00200 3. CABLE LAYING FROM MSR TO ESSENTIAL PANEL |  | 2020-06-20 | 2020-06-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0020 5. INSTALLATION OF NEW UPS DB IN LHS ELECTRICAL ROOM |  | 2020-05-11 | 2020-05-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00160 2. CABLE TRAY CONNECTION WITH NEW ESSENTIAL PANEL |  | 2020-06-15 | 2020-06-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00100 1. RELOCATION OF EARTH PIT AT FORECOURT GRADE LEVEL TO AREA |  | 2020-05-11 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0070 4. SHIFTING /LAYING CABLES FROM AHU's BLOWER LOCAL STARTER |  | 2020-05-22 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0040 3. CABLE TERMINATION & CHARGING HEATER PANEL (SHUTDOWN REQ |  | 2020-05-21 | 2020-05-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0030 2. LAYING THE INCOMING CABLE FROM MSR TO HEATER PANEL 2 |  | 2020-05-13 | 2020-05-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0010 1. DISCONNECTION AND SHIFTING OF HEATER PANEL 2 AT CORIDOR |  | 2020-05-11 | 2020-05-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0080 DISCONNECTION AND SHIFTING OF HEATER PANEL 3 AT CORIDOR B ( |  | 2020-06-10 | 2020-06-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00290 SHIFTING /LAYING CABLES FROM AHU's BLOWER LOCAL STARTER PA |  | 2020-06-23 | 2020-07-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00190 CABLE TERMINATION & CHARGING HEATER PANEL (SHUTDOWN REQUI |  | 2020-06-22 | 2020-06-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00180 LAYING THE INCOMING CABLE FROM MSR TO HEATER PANEL 3 |  | 2020-06-13 | 2020-06-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00500 SHIFTING /LAYING CABLES FROM AHU's HEATER TO BLOWER PANEL |  | 2020-07-27 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00420 CABLE TERMINATION & CHARGING BLOWER PANEL 1 & EPFC PANEL |  | 2020-07-25 | 2020-07-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00400 LAYING THE INCOMING CABLE FROM MSR TO BLOWER PANEL 1 |  | 2020-07-17 | 2020-07-24
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00320 DISCONNECTION AND SHIFTING OF BLOWER PANEL 1 & EPFC PANEL |  | 2020-07-14 | 2020-07-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00510 SHIFTING /LAYING CABLES FROM AHU's HEATER TO BLOWER PANEL |  | 2020-07-27 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00430 CABLE TERMINATION & CHARGING BLOWER PANEL |  | 2020-07-25 | 2020-07-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00410 LAYING THE INCOMING CABLE FROM MSR TO BLOWER PANEL 2 |  | 2020-07-17 | 2020-07-24
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00330 SHIFTING OF BLOWER PANEL 2 AT CORIDOR B ( GRID G'6A) |  | 2020-07-14 | 2020-07-16
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00470 CABLE LAYING FROM RETAIL PANELTO RETAIL STORE (THROUGH EXI |  | 2020-07-23 | 2020-08-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00380 CORE CUTTING AT DEPARTURE LEVEL SLAB FOR OUTGOING CABLE FR |  | 2020-07-22 | 2020-07-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00360 CABLE TERMINATION & CHARGING OF NEW RETAIL PANEL |  | 2020-07-22 | 2020-07-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00340 NEW INCOMING CABLE LAYING FROM SSB TO PANEL |  | 2020-07-14 | 2020-07-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00270 CABLE TRAY CONNECTION WITH PANEL |  | 2020-07-10 | 2020-07-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00260 NEW CABLE TRAY INSTALLATION WITH EARTHING AT MEZZANINE LEV |  | 2020-06-10 | 2020-07-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00120 INSTALLATION OF NEW RETAIL PANEL AT GRID D'2 |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00480 CABLE LAYING FROM RETAIL SHOPS AT DEPT LEVEL TO NEW PANELS |  | 2020-07-23 | 2020-08-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00370 CABLE TERMINATION & CHARGING OF NEW RETAIL PANEL-1 AND SMA |  | 2020-07-21 | 2020-07-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00350 NEW INCOMING CABLE LAYING FROM SSB TO PANEL |  | 2020-07-14 | 2020-07-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00280 CABLE TRAY CONNECTION WITH PANEL |  | 2020-07-10 | 2020-07-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00130 INSTALLATION OF NEW SMALL RETAIL PANEL AT GRID J'3 |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00110 INSTALLATION OF NEW RETAIL PANEL-1 AT GRID J'3 |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00450 CABLE TERMINATION & CHARGING OF SMOKE EXTRACTION PANEL |  | 2020-08-03 | 2020-08-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00440 NEW CABLE LAYING FROM MSR THROUGH BMA AREA TO SMOKE EXTRAC |  | 2020-07-10 | 2020-08-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00300 CABLE TRAY CONNECTION WITH PANEL |  | 2020-07-10 | 2020-07-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00140 INSTALLATION OF SMOKE EXTRACTION PANEL ( NEW) |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00520 CABLE TERMINATION & CHARGING OF UPS , UPS PANEL |  | 2020-08-10 | 2020-08-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00460 NEW CABLE LAYING FROM MSR THROUGH BMA AREA TO UPS |  | 2020-07-10 | 2020-08-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00390 CABLE TRAY CONNECTION WITH UPS , UPS OUTGOING PANEL |  | 2020-07-10 | 2020-07-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00240 SHIFTING & INSTALLATION OF EXISTING UPS WITH BATTERY BANK |  | 2020-06-29 | 2020-07-06
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00150 INSTALLATION OF NEW UPS OUTGOING PANEL ( GRID D'1) |  | 2020-06-06 | 2020-06-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00540 DISMANTLING OF EXISTING PANEL AT SERVICE MEZZANINE CORRIDO |  | 2020-08-17 | 2020-08-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00640 REMOVAL OF EXISTING PANEL , DB & ATS AT RHS ELECTRICAL ROOM |  | 2020-09-26 | 2020-09-29
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00630 TESTING & COMMISSIONING OF ELECTRICAL SYSTEM AT DEPARTURE L |  | 2020-09-21 | 2020-09-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00620 CABLE LAYING FROM DB TO EXISTING LIGHTING POINT AT ROOF CEIL |  | 2020-09-09 | 2020-09-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00610 CABLE LAYING FROM SMOKE EXTRACTION PANEL TO FANS AT ROOF AND |  | 2020-08-20 | 2020-09-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00600 CABLE LAYING FROM UPS PANEL AT MEZZANINE CORRIDOR C TO DB IN |  | 2020-09-03 | 2020-09-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00590 CABLE TRAY CONNECTION TO INSTALLED DB |  | 2020-09-02 | 2020-09-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00580 INSTALLATION OF 6 NOS DB & 3 NOS ATS AT PUFF PANEL |  | 2020-08-31 | 2020-09-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00560 CABLE TRAY INSTALLATION INSIDE CORECUT |  | 2020-08-17 | 2020-08-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00550 SLAB OPENING CUTOUT AT DEPARTURE SLAB |  | 2020-08-14 | 2020-08-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00250 CABLE TERMINATION & REMOVAL OF ZERO TOLERANCE PANEL |  | 2020-06-22 | 2020-07-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00170 LAYING OF CABLE FROM MSB TO T1D MAIN ELECTRICAL ROOM FOR ZTP |  | 2020-05-20 | 2020-06-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0090 NEW CABLE TRAY WITH EARTHING AND CABLE LAYING |  | 2020-05-20 | 2020-06-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0060 NEW PIPE LINE AND VALVES INSTALLATION INISDE SSB PUMP ROO |  | 2020-04-22 | 2020-06-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00430 TESTING AND COMMISSIONING OF FIRE FIGHTING SYSTEM |  | 2020-10-01 | 2020-10-03
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00410 SHIFTING & INSTALLATION OF DIESEL PUMP (HYDR AND SPR) FR |  | 2020-09-21 | 2020-09-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0040 DEMOLITION OF FOUNDATION, RAMP AND CONSTRUCTION OF NEW FO |  | 2020-04-04 | 2020-05-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00370 CHARGING OF T1D AND G+5 BUILDING USING ELECTRICAL AND JO |  | 2020-09-19 | 2020-09-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00360 FLUSHING OF FIRE WATER NETWORK |  | 2020-09-16 | 2020-09-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00340 SHIFTING & INSTALLATION OF JOCKEY PUMP (HYDR AND SPR) FR |  | 2020-09-09 | 2020-09-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0020 CIVIL AND FINISHING WORKS IN PUMP ROOM NEAR SSB |  | 2020-04-04 | 2020-04-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00190 CHARGING OF ZONE 28 AND 27 USING ELECT PUMP (WITH DG BAC |  | 2020-07-02 | 2020-07-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00170 COMMISSIONING OF ELECTRICAL PUMPSETS |  | 2020-06-24 | 2020-07-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00140 HYDROTEST |  | 2020-06-19 | 2020-06-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00130 CABLE TERMINATION AND EARTHING OF PUMPSETS |  | 2020-06-19 | 2020-06-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00120 SHIFTING & INSTALLATION OF ELECTRICAL MOTOR DRIVEN PUMP |  | 2020-06-16 | 2020-06-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00110 SHIFTING & INSTALLATION OF ELECTRICAL MOTOR DRIVEN PUMP |  | 2020-06-12 | 2020-06-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00100 SHIFTING & INSTALLATION OF EXISTING ELECTRICAL PANEL FRO |  | 2020-06-12 | 2020-06-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0010 DISMANTLING OF EXISTING FIRE PIPE & PUMPSET AT SSB BUILD |  | 2020-03-27 | 2020-04-03
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0080 PIPE LAYING UNDER RAMP FROM SSB PR TO EXISTING HYDRANT |  | 2020-05-12 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00300 PIPE LAYING FROM EXISTING HEADER AT GRID 11-J' TO GRID |  | 2020-08-14 | 2020-09-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0070 PIPE LAYING FROM SSB TO ZONE 28 ALARM CHECK VALVE |  | 2020-05-12 | 2020-06-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00150 PIPE LAYING FROM ZONE 28 ALARM CHECK VALVE TO ENTRY OF |  | 2020-06-10 | 2020-06-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00210 PIPE LAYING FROM SSB PUMP ROOM UPTO TUUNEL JUNCTION AT T |  | 2020-07-03 | 2020-08-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00240 SPRINKLER PIPE INSTALLATION |  | 2020-08-14 | 2020-08-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00230 HYDRANT PIPE INSTALLATION AT GRADE LEVEL |  | 2020-08-14 | 2020-08-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00330 SPRINKLER PIPE INSTALLATION WITH ZONE CONTROL VALVES |  | 2020-08-27 | 2020-09-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00310 HYDRANT PIPE INSTALLATION AT GRADE LEVEL |  | 2020-08-27 | 2020-09-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00260 SPINKLER PIPE INSTALLATION NEAR J2 TO EXISTING HEADER F |  | 2020-08-20 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00250 HYDRANT PIPE INSTALLATION ABOVE FALSE CEILING UPTO EXIST |  | 2020-08-20 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00390 SPINKLER PIPE INSTALLATION 3 NOS FROM GRID J4A TO ROOF C |  | 2020-08-27 | 2020-09-24
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00220 CORECUT FROM MEZZANINE SLAB TO DEPARTURE (NEAR GRID J4A) |  | 2020-08-19 | 2020-08-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00200 SHIFTING OF HYDRANT VALVE AT DEPARTURE GRID J3 - SHUTDOW |  | 2020-07-21 | 2020-07-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00180 NEW HYDRANT PIPE INSTALLATION |  | 2020-07-16 | 2020-07-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00160 CORECUT FROM MEZZANINE SLAB TO DEPARTURE (NEAR GRID J3) |  | 2020-07-15 | 2020-07-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00440 DISMANTLING OF FIRE PUMPROOM |  | 2020-09-26 | 2020-10-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00420 DISMANTLING OF FIRE PIPE AT DEPARTURE LEVEL |  | 2020-09-26 | 2020-10-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00400 CONNECTION OF NEWLY LAID SPRINKLER PIPE WITH EXISTING PIPE |  | 2020-09-25 | 2020-09-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00380 DISMANTLING OF EXTERNAL FIRE PIPE (OLD FIRE HYDRANT LOOP) |  | 2020-09-09 | 2020-09-19
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00350 CONNECTION OF NEWLY LAID SPRINKLER PIPE WITH EXISTING PIPE |  | 2020-09-14 | 2020-09-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00320 CONNECTION OF NEWLY LAID HYDRANT PIPE WITH EXISTING PIPE - |  | 2020-09-08 | 2020-09-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0050 LAYING OF PORTION OF CABLE TO FORM ALTERNATE LOOPS |  | 2020-05-11 | 2020-06-02
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0030 IDENTIFICATION OF ALL LOOPS CROSSING K GRID |  | 2020-03-31 | 2020-04-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00290 CLOSURE OF FDAS LOOPS 11 AND 13 GOING BEYOND GRID- K AFTER D |  | 2020-08-07 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00280 CLOSURE OF FDAS LOOP 10 GOING BEYOND GRID- K AFTER DISCONNEC |  | 2020-08-07 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00270 CLOSURE OF FDAS LOOP 1, 3 AND 16 GOING BEYOND GRID- K AFTER |  | 2020-08-07 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00130 RELOCATION OF SERVICES MOUNTED ON WALL ALONG K-GRID IN BMA ARE |  | 2020-08-14 | 2020-09-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0080 INSTALLATION OF FRESH AIR INTAKE THROUGH VIP LOUNGE AREA & CO |  | 2020-08-14 | 2020-08-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0070 INSTALL FRESH AIR INTAKE OVER WAITING AREA |  | 2020-08-20 | 2020-09-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0060 REMOVAL OF MAKE UP AIR DUCTS OF BMA SMOKE EXTRACTION SYSTEM A |  | 2020-07-20 | 2020-07-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0050 NEW FAN INSTALLATION AT CORRIDOR - A |  | 2020-07-13 | 2020-07-20
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00220 CONNECTION OF FAN DISCHARGE WITH EXISTING DUCTING AT CORRIDO |  | 2020-09-12 | 2020-09-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00190 CONNECTION OF FAN WITH NEW INSTALLED FRESH AIR DUCT AT CORRI |  | 2020-09-09 | 2020-09-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00160 SHIFT THE FAN OF CORRIDOR-A AT CORRIDOR-C |  | 2020-09-05 | 2020-09-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00120 DISCONNECTION & REMOVAL OF EXISTING FAN OF CORRIDORE - A |  | 2020-08-31 | 2020-09-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00110 REMOVAL OF AHU 22 SERVING TO RETAIL AREA FROM CORRIDOR - C A |  | 2020-08-24 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00100 CONNECTIONN OF NEW FAN DISCHARGE TO EXISTING FRESH AIR DUCT |  | 2020-08-29 | 2020-08-29
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0090 DISCONNECTION & REMOVAL OF EXISTING AHUs AT CORRIDOR C |  | 2020-08-11 | 2020-09-10
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0040 CHWP RISER FROM FORECOURT COLUMN TO BUILDING ENTRY (UNDER CEI |  | 2020-05-29 | 2020-06-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0030 CHWP FROM TUNNEL TO FORECOURT COLUMN |  | 2020-05-13 | 2020-05-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00260 DISMANTELING OF EXISTING CHWP |  | 2020-09-16 | 2020-09-26
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00250 INSULATION OF PIPE UPTO BUILDING ENTRY |  | 2020-06-16 | 2020-06-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00240 INSULATION OF CHWP |  | 2020-09-14 | 2020-09-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00230 CHARGING OF LINE AND TESTING AND COMMISSIONING OF HVAC SYSTE |  | 2020-09-14 | 2020-09-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00210 FINAL HYDROTEST OF CHWP |  | 2020-09-10 | 2020-09-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00200 HYDROTEST OF PIPE UPTO BUILDING ENTRY |  | 2020-06-12 | 2020-06-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0020 APPROVAL FOR RADIOGRAPHY TEST |  | 2020-04-27 | 2020-05-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00180 ADDITIONAL SUPPORT FOR CHWP RUNNING AT CEILING CLOSE TO K- G |  | 2020-08-14 | 2020-09-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00170 RADIOGRAPHY TEST OF CHWP |  | 2020-06-12 | 2020-06-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00150 DISCONNECTION & REMOVAL OF EXISTING AHUs AT CORRIDOR A AND B |  | 2020-08-07 | 2020-09-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00140 INSTALLATION OF CHWP INSIDE BUILDING AND CONNECTION TO NEW T |  | 2020-08-14 | 2020-09-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0010 TAPPING WORKS WITH EXISTING CHWP AND VALVE ARRANGEMENT |  | 2020-02-01 | 2020-02-14
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0090 COMISSIONING HNS-1 |  | 2020-09-01 | 2020-09-05
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0080 TESTING OF HEADER LINE |  | 2020-08-29 | 2020-08-31
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0070 SHIFTING & INSTALLATION OF ELECTRICAL PANEL FOR HNS-1 SYSTEM |  | 2020-08-22 | 2020-08-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0050 SHIFTING & INSTALLATION OF HNS-1 PUMP SET |  | 2020-08-14 | 2020-08-21
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0040 EXTERNAL PIPE LAYING UNDER RAMP FROM SSB TO GRID H11 & ZONE 2 |  | 2020-06-19 | 2020-07-23
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0030 ELECTRICAL TRAY, CABLES & TERMINATION |  | 2020-07-11 | 2020-07-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0020 INSTALLATION OF HEADER LINE FOR HNS-1 & 2 |  | 2020-06-23 | 2020-07-10
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0010 FOUNDATION OF HNS PUMPSET |  | 2020-06-12 | 2020-06-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0060 WATER SUPPLY PIPE INSTALLATION AT CORRIDOR A & C ( MEZZANINE) |  | 2020-06-19 | 2020-07-07
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00170 REMOVAL OF PLUMBING PIPES |  | 2020-09-12 | 2020-09-18
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00160 COMISSIONING HNS-2 |  | 2020-09-10 | 2020-09-11
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00150 SHIFTING & INSTALLATION OF ELECTRICAL PANEL FOR HNS-2 SYSTEM |  | 2020-09-07 | 2020-09-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00140 SHIFTING & INSTALLATION OF HNS-2 PUMP SET |  | 2020-09-07 | 2020-09-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00130 TESTING AND FLUSHING OF PIPELINE |  | 2020-08-26 | 2020-08-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00120 CONNECTION OF PIPE WITH EXISTING PIPE AT MEZZANINE ( CORRIDO |  | 2020-08-24 | 2020-08-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00110 WATER SUPPLY PIPE INSTALLATION FROM GRID H11 INSIDE VIP LOUN |  | 2020-08-14 | 2020-08-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00100 WATER SUPPLY PIPE INSTALLATION INSIDE BMA AREA |  | 2020-07-08 | 2020-07-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-90 SHIFTING OF DDC (2 No.s) AND WIRING TERMINATION |  | 2020-07-09 | 2020-07-25
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-80 NEW WIRING APART FROM VIP LOUNGE |  | 2020-06-09 | 2020-07-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-70 NEW CONDUITING WORK APART FROM VIP LOUNGE |  | 2020-05-05 | 2020-06-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-60 TRACING OF ALL ELV LOOPS |  | 2020-03-30 | 2020-05-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0060 DDC COMMISIONING |  | 2020-09-16 | 2020-09-22
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0050 SHIFTING OF DDC AND WIRING TERMINATION |  | 2020-09-02 | 2020-09-15
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0040 REPULLING OF WIRING |  | 2020-08-29 | 2020-09-01
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0030 CONDUITING WORK INSIDE VIP LOUNGE |  | 2020-08-07 | 2020-08-28
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-IT-00-0020 RELAYING OF CABLES FROM GF, MEZZANINE AND DEPARTURE LEVEL END |  | 2020-04-10 | 2020-06-08
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-IT-00-0010 DISMANTLING OF SCCR AT GF, MEZZANINE AND DEPARTURE FLOOR AND |  | 2020-03-24 | 2020-04-09
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0090 SHIFTING OF TM, CISF, L&F ROOM |  | 2020-08-06 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0080 SHIFTING OF VIP LOUNGE TO RESERVED LOUNGE & CEREMONIAL LOUNGE |  | 2020-08-07 | 2020-08-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0070 SHIFTING OF KITCHEN |  | 2020-08-07 | 2020-08-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0060 SHIFTING OF D-D FACILITY THROUGH SHUTTLE |  | 2020-08-07 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0050 SHIFTING OF TICKETING COUNTER |  | 2020-08-07 | 2020-08-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0040 SHIFTING OF F&B TO AREA 28 |  | 2020-08-07 | 2020-08-13
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0030 SHIFTING OF MEDICAL FACILITY- MEDANTA |  | 2020-07-30 | 2020-08-12
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0020 RELOCATION OF DISPATCH OFFICE / AIRPORT FACILITY TO ALTERNATE L |  | 2020-04-17 | 2020-04-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0010 CLOSURE OF PREMIER PLAZA LOUNGE AT GF |  | 2020-04-24 | 2020-04-30
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-AS-00-0020 INSTALLATION OF REMOVED LIFT AT ZONE 28 (FROM MAIN SCHEDULE) |  | 2020-05-14 | 2020-07-04
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-AS-00-0010 REMOVAL OF 1 LIFT FROM AREA NEAR VIP LOUNGE AND PPL |  | 2020-03-30 | 2020-04-28