## WBS_Master_Physical
Project | Consultant_Contractor | Package | SubPackage_1 | SubPackage_2 | SubPackage_3 | SubPackage_4 | SubPackage_5 | Activity | WBS_Points | UoM | Scope | Discipline | Commodity
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0040 RETAIL AND F&B | 4800 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0030 MEP AND IT | 4800 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0020 STRUCTURAL | 4800 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-CD-00-0010 ARCHITECTURAL | 4800 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0120 DEMOLITION SCHEME (AGENCY) | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0110 RETROFITTING WORKS | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0100 TEMP FACADE | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0090 ARCHITECTURAL | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0080 AIRPORT SYSTEMS | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0070 IT (BY DIAL) | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0060 STRUCTURAL | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0050 HVAC | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0040 PHE | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0030 FPS AND FDAS | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0020 ELECTRICAL | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DS-00-0010 ELV | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0120 DEMOLITION SCHEME | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0110 RETROFITTING WORKS | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0100 TEMP FACADE | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0090 ARCHITECTURAL | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0080 AIRPORT SYSTEMS | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0070 IT (BY DIAL) | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0060 STRUCTURAL | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0050 HVAC | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0040 PHE | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0030 FPS AND FDAS | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0020 ELECTRICAL | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-DA-00-0010 ELV | 1500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0120 DEMOLITION SCHEME | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0110 RETROFITTING WORKS | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0100 TEMP FACADE | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0090 ARCHITECTURAL | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0080 AIRPORT SYSTEMS | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0070 IT (BY DIAL) | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0060 STRUCTURAL | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0050 HVAC | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0040 PHE | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0030 FPS AND FDAS | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0020 ELECTRICAL | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Engineering | K Grid | K Grid | DI-KG-EG-GF-00-0010 ELV | 1400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00130 DEMOLITION AGENCY - STEEL AND CONCRETE WORKS | 9000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00100 AGENCY FOR RETROFITTING WORKS- COLUMN STRENGTHENING | 9000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0050 TEMP. FAÇADE AGENCY | 18000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0090 AGENCY FOR HVAC WORK | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0080 AGENCY FOR FIRE ALARM SYSTEM | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0070 AGENCY FOR ELECTRICAL WORK | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0060 AGENCY FOR FIRE FIGHTING WORK | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0040 AGENCY FOR BMS WORK | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0010 AGENCY FOR PHE WORK | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00120 AGENCY FOR FINISHES- RESERVED LOUNGE,TM COMPLEX,TICKET COUNT | 9000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-00110 AGENCY FOR FINISHES- TOILET | 9000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0030 AGENCY FOR ELEVATOR - MODIFICATION WORK | 6000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-PO-00-0020 AGENCY FOR ELEVATOR - NEW ( PRM LIFT) | 6000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0080 DUCT | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0070 CABLE | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0060 PANEL | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0050 AUTOMATIC TRANSFER SWITCH | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00130 VALVES | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00120 PIPES | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00110 VENTILATION FAN | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0090 ELECTRICAL LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0030 FIRE FIGHTING LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0020 BMS LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00140 HVAC LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-00100 FIRE ALARM LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0010 PHE LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-MC-00-0040 ELEVATOR | 24000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00120 RETROFITTING WORKS | 21000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0010 MOBILISATION OF DEMOLITION AGENCY | 21000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00210 HARD BARRICADING | 14000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00200 SOFT PANELS | 14000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00190 PUFF PANELS | 14000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0080 PIPES | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0050 DUCT | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00160 VENTILATION FANS | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00150 AUTOMATIC TRANSFER SWITCH | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00140 PANEL | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00110 CABLE | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00100 VALVES | 1714.2857 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0090 HVAC LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0070 FIRE ALARM LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0060 ELECTRICAL LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0040 FIRE FIGHTING LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0030 BMS LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-0020 PHE LOW SIDE | 2000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00180 RESERVED LOUNGE,TM COMPLEX,TICKET COUNTER, L&F ROOM FINISHES | 21000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00170 FINISHES | 21000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Procurement | K Grid | K Grid | DI-KG-PR-DL-00-00130 ELEVATOR - NEW ( PRM LIFT) | 24000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0070 PUFF PANEL BARRICADE AT MEZZANINE CORRIDOR - A&C | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0060 PUFF PANEL BARRICADE AT DEPARTURE | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0050 SOFT PANEL BARRICADE AT DEPARTURE | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0040 HARD BARRICADE AROUND 2 SIDES OF T1D BUILDING AT FORECOURT & AI | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0030 PUFF PANEL BARRICADE BOARDING GATE AREA - APRON LEVEL | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0020 SOFT PANEL BARRICADE BOARDING GATE AREA - APRON LEVEL | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-TF-00-0010 PUFF PANEL BARRICADE AT BMA | 9142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0090 DISMANTLING OF AREA 2 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0080 DISMANTLING OF AREA 3 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0070 DISMANTLING OF AREA 1 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0060 STRENGTHENING OF LIFT COLUMN AT K-2 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0050 STRENGTHENING OF LIFT COLUMN AT K-9 SUPERSTRUCTURE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0040 STRENGTHENING OF LIFT COLUMN AT K-9 SUBSTRUCTURE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0030 LOCAL BARRICADE AND CLOSURE OF F&B AT GRID K-9 IN TICKET COUNTE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0020 CONVERSION OF DDC AT GRID K-9 ON MANUAL MODE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SD-00-0010 LOCAL SHIFTING OF EXTRACT FAN AT GRID K-9 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0080 BLOCK WALL & SLAB FOR WASH BASIN | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0060 BREAKING OF FALSE CEILING | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0050 BREAKING OF TILE | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0040 BARRICATION OF BMA TOILET | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00200 FINISHING WORK INCL MEP 3RD FIX | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00150 PLASTER & WALL TILING | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00120 TESTING OF PHE LINE | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00100 CHASING AND LAYING OF PHE PIPE | 500 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00380 FINISHING WORK INCL MEP 3RD FIX | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00330 PLASTER & WALL TILING | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00290 TESTING OF PHE LINE | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00280 CHASING AND LAYING OF PHE PIPE | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00270 BLOCK WALL & SLAB FOR WASH BASIN | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00240 BREAKING OF BLOCK WALL FOR MAKING WORKMEN ACCESS FROM BMA | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00210 AREA BARRICATION & REMOVAL OF SEATS | 571.4286 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00300 MODIFICATION WORKS - FINISHING | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00220 MODIFICATION WORKS - MEP | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00170 SLAB CUTOUT AND ACCESS STAIRCASE FOR COR-C ON RHS | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00160 CONNECTING PLATFORM TO EXIT STAIRCASE ST-03 FROM MEZZANINE S | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00480 FINISHING WORK INCL MEP 3RD FIX | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00470 PLASTER & WALL TILING | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00460 TESTING OF PHE LINE | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00450 CHASING AND LAYING OF PHE PIPE | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00420 BLOCK WALL & SLAB FOR WASH BASIN | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00410 BREAKING OF FALSE CEILING | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00400 BREAKING OF TILE | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00390 BARRICATION OF PRE-SHA TOILET | 1000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00350 TESTING & COMMISSIONING OF PRM LIFT | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00340 LIFT INSTALLATION | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0030 BMA AREA WALL DEMOLITION OF LIFT INSTALLATION ACCESS | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0020 BARRICATION | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00190 ELECTRICAL SUPPLY , SHAFT LIGHTING ETC | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00180 LIFT SHAFT & PIT CONNECTION (CIVIL WORKS) | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0010 APPROVAL FOR BMA AREA WALL DEMOLITION/BARRICATION | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0090 IT WORKS (DIAL) | 2666.6667 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-0070 PROVISION OF POWER SOURCE AT NEW LOCATION | 2666.6667 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00130 SHIFTING OF MACHINE | 2666.6667 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00430 INTERNAL FINISHING WORKS | 1600 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00310 IT WORKS | 1600 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00260 ELECTRICAL WORKS | 1600 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00250 CIVIL WORKS (PARTITION INSTALLATION AND CIELING WORKS) | 1600 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00140 BARRICATION WORKS | 1600 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00440 INTERNAL FINISHING WORKS | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00370 MEP WORKS | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00360 IT WORKS | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00320 CIVIL WORKS (PARTITION INSTALLATION AND CIELING WORKS) | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00230 REMOVAL OF CENTRAL STAIR CASE & SLAB CASTING | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-CF-00-00110 BARRICATION | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0090 1. INSTALLATION OF NEW ESSENTIAL PANEL AT BMA | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0060 5. TRACING OF EXISTING FLOOR RACEWAY / CONDUIT ABOVE FALSE CE | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00570 7. REMOVAL OF DBs FEEDING TO VIP CORRIDOR | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00530 7. DISCONNECTION AND REMOVAL OF EXISTING PANEL / DBs at RHS | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0050 1. CABLE TRAY LAYING WITH EARTHING FROM MSR TO NEW ESSENTIAL | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00490 8. DISMANTLING OF KITCHEN PANEL | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00310 6. TRANSFER LOAD ( VRV, AIR CURTAINS AND STARTER) TO NEW ESS | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00230 7. 60 KVA UPS DISCONNECTION AT RHS ROOM | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00220 4. CABLE TERMINATION & CHARGING OF ESSENTIAL PANEL | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00210 6. TRANSFER LOAD ( EMERGENCY LIGHTS, SL DOOR, FIDS, GATE COU | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00200 3. CABLE LAYING FROM MSR TO ESSENTIAL PANEL | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0020 5. INSTALLATION OF NEW UPS DB IN LHS ELECTRICAL ROOM | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00160 2. CABLE TRAY CONNECTION WITH NEW ESSENTIAL PANEL | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00100 1. RELOCATION OF EARTH PIT AT FORECOURT GRADE LEVEL TO AREA | 1142.8571 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0070 4. SHIFTING /LAYING CABLES FROM AHU's BLOWER LOCAL STARTER | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0040 3. CABLE TERMINATION & CHARGING HEATER PANEL (SHUTDOWN REQ | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0030 2. LAYING THE INCOMING CABLE FROM MSR TO HEATER PANEL 2 | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0010 1. DISCONNECTION AND SHIFTING OF HEATER PANEL 2 AT CORIDOR | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-0080 DISCONNECTION AND SHIFTING OF HEATER PANEL 3 AT CORIDOR B ( | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00290 SHIFTING /LAYING CABLES FROM AHU's BLOWER LOCAL STARTER PA | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00190 CABLE TERMINATION & CHARGING HEATER PANEL (SHUTDOWN REQUI | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00180 LAYING THE INCOMING CABLE FROM MSR TO HEATER PANEL 3 | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00500 SHIFTING /LAYING CABLES FROM AHU's HEATER TO BLOWER PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00420 CABLE TERMINATION & CHARGING BLOWER PANEL 1 & EPFC PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00400 LAYING THE INCOMING CABLE FROM MSR TO BLOWER PANEL 1 | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00320 DISCONNECTION AND SHIFTING OF BLOWER PANEL 1 & EPFC PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00510 SHIFTING /LAYING CABLES FROM AHU's HEATER TO BLOWER PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00430 CABLE TERMINATION & CHARGING BLOWER PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00410 LAYING THE INCOMING CABLE FROM MSR TO BLOWER PANEL 2 | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00330 SHIFTING OF BLOWER PANEL 2 AT CORIDOR B ( GRID G'6A) | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00470 CABLE LAYING FROM RETAIL PANELTO RETAIL STORE (THROUGH EXI | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00380 CORE CUTTING AT DEPARTURE LEVEL SLAB FOR OUTGOING CABLE FR | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00360 CABLE TERMINATION & CHARGING OF NEW RETAIL PANEL | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00340 NEW INCOMING CABLE LAYING FROM SSB TO PANEL | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00270 CABLE TRAY CONNECTION WITH PANEL | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00260 NEW CABLE TRAY INSTALLATION WITH EARTHING AT MEZZANINE LEV | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00120 INSTALLATION OF NEW RETAIL PANEL AT GRID D'2 | 253.9683 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00480 CABLE LAYING FROM RETAIL SHOPS AT DEPT LEVEL TO NEW PANELS | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00370 CABLE TERMINATION & CHARGING OF NEW RETAIL PANEL-1 AND SMA | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00350 NEW INCOMING CABLE LAYING FROM SSB TO PANEL | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00280 CABLE TRAY CONNECTION WITH PANEL | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00130 INSTALLATION OF NEW SMALL RETAIL PANEL AT GRID J'3 | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00110 INSTALLATION OF NEW RETAIL PANEL-1 AT GRID J'3 | 296.2963 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00450 CABLE TERMINATION & CHARGING OF SMOKE EXTRACTION PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00440 NEW CABLE LAYING FROM MSR THROUGH BMA AREA TO SMOKE EXTRAC | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00300 CABLE TRAY CONNECTION WITH PANEL | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00140 INSTALLATION OF SMOKE EXTRACTION PANEL ( NEW) | 444.4444 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00520 CABLE TERMINATION & CHARGING OF UPS , UPS PANEL | 355.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00460 NEW CABLE LAYING FROM MSR THROUGH BMA AREA TO UPS | 355.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00390 CABLE TRAY CONNECTION WITH UPS , UPS OUTGOING PANEL | 355.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00240 SHIFTING & INSTALLATION OF EXISTING UPS WITH BATTERY BANK | 355.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00150 INSTALLATION OF NEW UPS OUTGOING PANEL ( GRID D'1) | 355.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00540 DISMANTLING OF EXISTING PANEL AT SERVICE MEZZANINE CORRIDO | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00640 REMOVAL OF EXISTING PANEL , DB & ATS AT RHS ELECTRICAL ROOM | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00630 TESTING & COMMISSIONING OF ELECTRICAL SYSTEM AT DEPARTURE L | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00620 CABLE LAYING FROM DB TO EXISTING LIGHTING POINT AT ROOF CEIL | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00610 CABLE LAYING FROM SMOKE EXTRACTION PANEL TO FANS AT ROOF AND | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00600 CABLE LAYING FROM UPS PANEL AT MEZZANINE CORRIDOR C TO DB IN | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00590 CABLE TRAY CONNECTION TO INSTALLED DB | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00580 INSTALLATION OF 6 NOS DB & 3 NOS ATS AT PUFF PANEL | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00560 CABLE TRAY INSTALLATION INSIDE CORECUT | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00550 SLAB OPENING CUTOUT AT DEPARTURE SLAB | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00250 CABLE TERMINATION & REMOVAL OF ZERO TOLERANCE PANEL | 8000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-EL-00-00170 LAYING OF CABLE FROM MSB TO T1D MAIN ELECTRICAL ROOM FOR ZTP | 8000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0090 NEW CABLE TRAY WITH EARTHING AND CABLE LAYING | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0060 NEW PIPE LINE AND VALVES INSTALLATION INISDE SSB PUMP ROO | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00430 TESTING AND COMMISSIONING OF FIRE FIGHTING SYSTEM | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00410 SHIFTING & INSTALLATION OF DIESEL PUMP (HYDR AND SPR) FR | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0040 DEMOLITION OF FOUNDATION, RAMP AND CONSTRUCTION OF NEW FO | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00370 CHARGING OF T1D AND G+5 BUILDING USING ELECTRICAL AND JO | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00360 FLUSHING OF FIRE WATER NETWORK | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00340 SHIFTING & INSTALLATION OF JOCKEY PUMP (HYDR AND SPR) FR | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0020 CIVIL AND FINISHING WORKS IN PUMP ROOM NEAR SSB | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00190 CHARGING OF ZONE 28 AND 27 USING ELECT PUMP (WITH DG BAC | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00170 COMMISSIONING OF ELECTRICAL PUMPSETS | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00140 HYDROTEST | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00130 CABLE TERMINATION AND EARTHING OF PUMPSETS | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00120 SHIFTING & INSTALLATION OF ELECTRICAL MOTOR DRIVEN PUMP | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00110 SHIFTING & INSTALLATION OF ELECTRICAL MOTOR DRIVEN PUMP | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00100 SHIFTING & INSTALLATION OF EXISTING ELECTRICAL PANEL FRO | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0010 DISMANTLING OF EXISTING FIRE PIPE & PUMPSET AT SSB BUILD | 209.1503 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0080 PIPE LAYING UNDER RAMP FROM SSB PR TO EXISTING HYDRANT | 888.8889 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00300 PIPE LAYING FROM EXISTING HEADER AT GRID 11-J' TO GRID | 888.8889 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0070 PIPE LAYING FROM SSB TO ZONE 28 ALARM CHECK VALVE | 888.8889 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00150 PIPE LAYING FROM ZONE 28 ALARM CHECK VALVE TO ENTRY OF | 888.8889 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00210 PIPE LAYING FROM SSB PUMP ROOM UPTO TUUNEL JUNCTION AT T | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00240 SPRINKLER PIPE INSTALLATION | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00230 HYDRANT PIPE INSTALLATION AT GRADE LEVEL | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00330 SPRINKLER PIPE INSTALLATION WITH ZONE CONTROL VALVES | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00310 HYDRANT PIPE INSTALLATION AT GRADE LEVEL | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00260 SPINKLER PIPE INSTALLATION NEAR J2 TO EXISTING HEADER F | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00250 HYDRANT PIPE INSTALLATION ABOVE FALSE CEILING UPTO EXIST | 1333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00390 SPINKLER PIPE INSTALLATION 3 NOS FROM GRID J4A TO ROOF C | 533.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00220 CORECUT FROM MEZZANINE SLAB TO DEPARTURE (NEAR GRID J4A) | 533.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00200 SHIFTING OF HYDRANT VALVE AT DEPARTURE GRID J3 - SHUTDOW | 533.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00180 NEW HYDRANT PIPE INSTALLATION | 533.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00160 CORECUT FROM MEZZANINE SLAB TO DEPARTURE (NEAR GRID J3) | 533.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00440 DISMANTLING OF FIRE PUMPROOM | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00420 DISMANTLING OF FIRE PIPE AT DEPARTURE LEVEL | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00400 CONNECTION OF NEWLY LAID SPRINKLER PIPE WITH EXISTING PIPE | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00380 DISMANTLING OF EXTERNAL FIRE PIPE (OLD FIRE HYDRANT LOOP) | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00350 CONNECTION OF NEWLY LAID SPRINKLER PIPE WITH EXISTING PIPE | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00320 CONNECTION OF NEWLY LAID HYDRANT PIPE WITH EXISTING PIPE - | 1777.7778 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0050 LAYING OF PORTION OF CABLE TO FORM ALTERNATE LOOPS | 6400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-0030 IDENTIFICATION OF ALL LOOPS CROSSING K GRID | 6400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00290 CLOSURE OF FDAS LOOPS 11 AND 13 GOING BEYOND GRID- K AFTER D | 6400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00280 CLOSURE OF FDAS LOOP 10 GOING BEYOND GRID- K AFTER DISCONNEC | 6400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-FS-00-00270 CLOSURE OF FDAS LOOP 1, 3 AND 16 GOING BEYOND GRID- K AFTER | 6400 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00130 RELOCATION OF SERVICES MOUNTED ON WALL ALONG K-GRID IN BMA ARE | 21333.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0080 INSTALLATION OF FRESH AIR INTAKE THROUGH VIP LOUNGE AREA & CO | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0070 INSTALL FRESH AIR INTAKE OVER WAITING AREA | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0060 REMOVAL OF MAKE UP AIR DUCTS OF BMA SMOKE EXTRACTION SYSTEM A | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0050 NEW FAN INSTALLATION AT CORRIDOR - A | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00220 CONNECTION OF FAN DISCHARGE WITH EXISTING DUCTING AT CORRIDO | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00190 CONNECTION OF FAN WITH NEW INSTALLED FRESH AIR DUCT AT CORRI | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00160 SHIFT THE FAN OF CORRIDOR-A AT CORRIDOR-C | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00120 DISCONNECTION & REMOVAL OF EXISTING FAN OF CORRIDORE - A | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00110 REMOVAL OF AHU 22 SERVING TO RETAIL AREA FROM CORRIDOR - C A | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00100 CONNECTIONN OF NEW FAN DISCHARGE TO EXISTING FRESH AIR DUCT | 2133.3333 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0090 DISCONNECTION & REMOVAL OF EXISTING AHUs AT CORRIDOR C | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0040 CHWP RISER FROM FORECOURT COLUMN TO BUILDING ENTRY (UNDER CEI | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0030 CHWP FROM TUNNEL TO FORECOURT COLUMN | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00260 DISMANTELING OF EXISTING CHWP | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00250 INSULATION OF PIPE UPTO BUILDING ENTRY | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00240 INSULATION OF CHWP | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00230 CHARGING OF LINE AND TESTING AND COMMISSIONING OF HVAC SYSTE | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00210 FINAL HYDROTEST OF CHWP | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00200 HYDROTEST OF PIPE UPTO BUILDING ENTRY | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0020 APPROVAL FOR RADIOGRAPHY TEST | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00180 ADDITIONAL SUPPORT FOR CHWP RUNNING AT CEILING CLOSE TO K- G | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00170 RADIOGRAPHY TEST OF CHWP | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00150 DISCONNECTION & REMOVAL OF EXISTING AHUs AT CORRIDOR A AND B | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-00140 INSTALLATION OF CHWP INSIDE BUILDING AND CONNECTION TO NEW T | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-HV-00-0010 TAPPING WORKS WITH EXISTING CHWP AND VALVE ARRANGEMENT | 1422.2222 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0090 COMISSIONING HNS-1 | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0080 TESTING OF HEADER LINE | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0070 SHIFTING & INSTALLATION OF ELECTRICAL PANEL FOR HNS-1 SYSTEM | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0050 SHIFTING & INSTALLATION OF HNS-1 PUMP SET | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0040 EXTERNAL PIPE LAYING UNDER RAMP FROM SSB TO GRID H11 & ZONE 2 | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0030 ELECTRICAL TRAY, CABLES & TERMINATION | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0020 INSTALLATION OF HEADER LINE FOR HNS-1 & 2 | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0010 FOUNDATION OF HNS PUMPSET | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-0060 WATER SUPPLY PIPE INSTALLATION AT CORRIDOR A & C ( MEZZANINE) | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00170 REMOVAL OF PLUMBING PIPES | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00160 COMISSIONING HNS-2 | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00150 SHIFTING & INSTALLATION OF ELECTRICAL PANEL FOR HNS-2 SYSTEM | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00140 SHIFTING & INSTALLATION OF HNS-2 PUMP SET | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00130 TESTING AND FLUSHING OF PIPELINE | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00120 CONNECTION OF PIPE WITH EXISTING PIPE AT MEZZANINE ( CORRIDO | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00110 WATER SUPPLY PIPE INSTALLATION FROM GRID H11 INSIDE VIP LOUN | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-PH-00-00100 WATER SUPPLY PIPE INSTALLATION INSIDE BMA AREA | 3555.5556 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-90 SHIFTING OF DDC (2 No.s) AND WIRING TERMINATION | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-80 NEW WIRING APART FROM VIP LOUNGE | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-70 NEW CONDUITING WORK APART FROM VIP LOUNGE | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-60 TRACING OF ALL ELV LOOPS | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0060 DDC COMMISIONING | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0050 SHIFTING OF DDC AND WIRING TERMINATION | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0040 REPULLING OF WIRING | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-LC-00-0030 CONDUITING WORK INSIDE VIP LOUNGE | 4000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-IT-00-0020 RELAYING OF CABLES FROM GF, MEZZANINE AND DEPARTURE LEVEL END | 16000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-IT-00-0010 DISMANTLING OF SCCR AT GF, MEZZANINE AND DEPARTURE FLOOR AND | 16000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0090 SHIFTING OF TM, CISF, L&F ROOM | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0080 SHIFTING OF VIP LOUNGE TO RESERVED LOUNGE & CEREMONIAL LOUNGE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0070 SHIFTING OF KITCHEN | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0060 SHIFTING OF D-D FACILITY THROUGH SHUTTLE | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0050 SHIFTING OF TICKETING COUNTER | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0040 SHIFTING OF F&B TO AREA 28 | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0030 SHIFTING OF MEDICAL FACILITY- MEDANTA | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0020 RELOCATION OF DISPATCH OFFICE / AIRPORT FACILITY TO ALTERNATE L | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-SF-00-0010 CLOSURE OF PREMIER PLAZA LOUNGE AT GF | 7111.1111 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-AS-00-0020 INSTALLATION OF REMOVED LIFT AT ZONE 28 (FROM MAIN SCHEDULE) | 32000 | % | 100 | LT | WEIGHTAGE
K-Grid, DIAL | L&T | K Grid | K Grid | K Grid | Construction | K Grid | K Grid | DI-KG-CO-AS-00-0010 REMOVAL OF 1 LIFT FROM AREA NEAR VIP LOUNGE AND PPL | 32000 | % | 100 | LT | WEIGHTAGE